# Change Request Form

Project Name: Syntra Mobile Commerce Platform Change Request ID: CR-001 Date Submitted: August 7, 2025

### 1. Requester Information

Requested By: Anjali Verma Title: Chief Marketing Officer (CMO) Department: Marketing

### 2. Change Description

Summary: Add a "User Reviews and Ratings" feature to the v1.0 scope of the Syntra mobile app.

Detailed Description: This change involves implementing a system to allow registered users to submit product reviews and star ratings (1-5 stars). The feature should include:

- Displaying the average star rating on the Product Listing Page (PLP) and Product Detail Page (PDP).

- A dedicated "Reviews" section on the PDP showing all user-submitted reviews.

- A form for users to write a review and submit a rating for a product they have purchased.

- A basic moderation capability in the admin panel for the customer support team to manage and approve reviews.

### 3. Business Justification

Reason for Change: Recent analysis of competitor apps shows that user-generated reviews are a key driver of conversion, increasing it by an estimated 10-15%. This "social proof" is critical for building trust with new customers and helping them make purchasing decisions. Our current mobile website data shows that products with user reviews have a significantly higher add-to-cart rate. Deferring this feature until a later version puts us at a competitive disadvantage from day one and misses a key opportunity to maximize launch ROI.

### 4. Impact Analysis (Initial Assessment by PM)

- Scope: This represents a significant scope increase. It introduces new UI/UX components, new API endpoints, database schema modifications, and new admin panel functionality. This was explicitly listed as "Out of Scope" in the PRD.

- Schedule: Estimated impact is an addition of 4 weeks to the development and testing timeline.

  - 1 week for Design & Prototyping.

  - 2 weeks for Development (frontend, backend, admin panel).

  - 1 week for dedicated Testing & Bug-fixing. This will push the forecasted launch date from December 1, 2025, to approximately December 29, 2025, missing the peak holiday shopping window.

- Budget: Estimated cost increase of ₹12 Lakhs.

  - Additional 4 weeks of development team effort (4 developers @ ₹2 Lakhs/week) = ₹8 Lakhs.

  - Additional 4 weeks of QA effort (2 testers @ ₹1 Lakh/week) = ₹4 Lakhs. This would increase the total project budget from ₹75 Lakhs to ₹87 Lakhs.

- Resources: No new resources are required, but the engagement of the current development and QA teams will be extended by 4 weeks. This may impact their availability for subsequent projects.

### 5. Recommendation

PM Recommendation: 🟡 Proceed with Caution While the business value is clear, the impact on the schedule and budget is significant. The biggest strategic concern is missing the primary holiday shopping season. Option A (Recommended): Approve the change, but re-scope it for a "fast-follow" release in January. This allows the core app to launch on time and on budget, capturing holiday sales, while delivering this key feature shortly after. Option B: Approve the change and accept the revised schedule and budget, understanding the risk of launching post-holidays.

### 6. Approval

This change requires approval from the Project Sponsor, CFO, and COO due to its impact on scope, budget, and operations.

| Stakeholder | Title | Approval Status | Signature | Date |
| --- | --- | --- | --- | --- |
| Anjali Verma | CMO | ✅ Approved | Anjali Verma | Aug 7, 2025 |
| Sameer Shah | CFO | ⚪ Pending |  |  |
| Meera Desai | COO | ⚪ Pending |  |  |