# Detailed Project Estimate: Syntra App

Project: Syntra Mobile Commerce Platform Methodology: Waterfall Prepared By: [Your Name], Project Manager Currency: USD ($)

### 1. Executive Summary

This document provides a detailed, bottom-up cost and time estimate for the Syntra project, assuming a distributed team model with leadership and key roles in the US and development/QA resources in India. The total estimated cost is $252,570 over a projected timeline of 26 weeks (6.5 months). This estimate is based on a detailed breakdown of work phases, blended resource rates, and a standard contingency buffer.

### 2. Time & Duration Estimate

The project is broken down into five distinct phases, followed by deployment. The duration remains unchanged.

| Phase | Duration (Weeks) | Key Activities |
| --- | --- | --- |
| 1. Requirements & Analysis | 4 | Project Charter, PRD, Stakeholder Workshops |
| 2. Design | 4 | Wireframes, High-Fidelity Mockups, UI/UX Specs |
| 3. Development | 12 | Core application coding, API development, integrations |
| 4. Testing & UAT | 4 | Functional, Performance, Security, User Acceptance |
| 5. Deployment | 2 | App Store submission, server go-live, launch support |
| Total Project Duration | 26 Weeks |  |

### 3. Cost Estimate Breakdown

Costs are broken down by project phase. All costs are in USD.

#### 3.1 Personnel Costs

Based on blended monthly rates for a distributed team (US & India). Assumes PM, Dev Lead, Designer, and QA Lead are US-based; all other developers and testers are India-based.

| Phase | Duration | Resources & Allocation | Estimated Cost (USD) |
| --- | --- | --- | --- |
| 1. Requirements | 4 Weeks | PM (1), Dev Lead (0.5), Designer (0.5) | $20,000 |
| 2. Design | 4 Weeks | PM (1), Designer (1), Dev Lead (0.5), Frontend Devs (0.5) | $28,000 |
| 3. Development | 12 Weeks | PM (1), Dev Lead (1), iOS Dev (1), Android Dev (1), Backend Dev (1), Designer (0.25) | $108,000 |
| 4. Testing & UAT | 4 Weeks | PM (1), QA Lead (1), QA Tester (1), Devs (0.5 for bug fixing) | $26,000 |
| 5. Deployment | 2 Weeks | PM (1), Dev Lead (1), Devs (1), QA Lead (0.5) | $18,875 |
| Total Personnel Cost |  |  | $200,875 |

#### 3.2 Other Direct Costs

Based on an exchange rate of 1 USD = 83 INR.

| Item | Description | Estimated Cost (USD) |
| --- | --- | --- |
| Software & Tools | Licenses for Jira, Figma, testing tools, etc. | $1,200 |
| Infrastructure | Server hosting (e.g., AWS/Azure) for the first year. | $6,000 |
| Third-Party Services | Payment gateway setup fees, analytics platform subscription. | $2,400 |
| Total Other Costs |  | $9,600 |

### 4. Total Project Cost Summary

| Category | Amount (USD) |
| --- | --- |
| Total Personnel Cost | $200,875 |
| Total Other Direct Costs | $9,600 |
| Subtotal | $210,475 |
| Contingency (20%) | $42,095 |
| Grand Total Estimated Cost | $252,570 |

Note on Contingency: A 20% contingency fund is included to cover unforeseen risks, minor scope changes, or unexpected complexities, which is standard practice for a project of this nature. This ensures the project has the necessary financial buffer to handle challenges without requiring immediate re-approval for minor overruns.