# Project Status Report

## Syntra Mobile Commerce Platform

Project Manager: Sumedha K Reporting Period: Week Ending: August 29, 2025

### 1. Overall Status: 🟡 At Risk

Executive Summary: Development of core application features is progressing well and is largely on schedule. The front-end team has completed the user browsing and shopping cart experience. However, the project schedule is now at risk due to a delay in the delivery of the final Inventory Management API from the backend IT team. This dependency blocks the upcoming work on the checkout and order placement functionality. Mitigation plans are in effect, but this issue requires close monitoring.

### 2. Key Accomplishments (This Period)

- Shopping Cart Implemented: Completed the development of the shopping cart feature (PBI-301, PBI-302). Users can now add, view, and manage items in their cart.

- Search & Filter Logic: Finalized the backend logic for product search and filtering (PBI-203, PBI-205). The UI is now connected to a functional search endpoint.

- User Profile Foundation: Built the basic user profile management screen where users will be able to manage shipping addresses (PBI-104).

- Technical Enabler: Completed the initial database schema setup for handling orders (related to PBI-501).

### 3. Activities Planned (Next Period)

- Begin Checkout Flow: Commence development on the checkout user interface, starting with the shipping address selection screen (PBI-303).

- Payment Gateway Integration: Begin technical integration of the Razorpay payment gateway SDK (PBI-503).

- Wishlist UI: Start UI development for the Wishlist feature (PBI-308).

- API Dependency Follow-up: Continue daily syncs with the IT team to get an updated delivery timeline for the Inventory API.

### 4. Project Health Metrics

| Area | Status | Comments |
| --- | --- | --- |
| Schedule | 🟡 At Risk | The 2-week delay in the Inventory API delivery puts the 'Development Complete' milestone at risk. |
| Budget | 🟢 On Track | Project spend is currently at 45% of the total budget, which aligns with the project plan. |
| Scope | 🟢 On Track | No scope changes have been requested or made. The team remains focused on v1.0 features. |
| Resources | 🟢 On Track | The project is fully staffed, and there are no resource constraints at this time. |

### 5. Key Risks & Issues

| ID | Risk / Issue | Impact | Mitigation Plan & Owner |
| --- | --- | --- | --- |
| R-01 | DELAY: The Inventory Management API delivery is delayed by an estimated 2 weeks. This is a critical dependency for the checkout process. | High | The development team is building the checkout flow using mock data to avoid a complete stoppage. Holding daily check-ins with Rohan Gupta's team for progress updates. Owner: Sumedha K |
| R-02 | RISK: The documentation for the selected payment gateway is proving to be less comprehensive than expected, which may slow down the integration task. | Med | A senior developer has been assigned to spike the integration and work directly with the gateway's technical support this week to clarify all queries. Owner: Dev Team Lead |

### 6. Milestone Tracker

| Milestone | Planned Date | Forecast Date | Status |
| --- | --- | --- | --- |
| Project Kick-off | Jun 2, 2025 | Jun 2, 2025 | ✅ Complete |
| Design & Analysis Complete | Jul 1, 2025 | Jul 1, 2025 | ✅ Complete |
| Development Complete | Oct 15, 2025 | Oct 29, 2025 | 🟡 At Risk |
| Testing & UAT Complete | Nov 15, 2025 | Nov 29, 2025 | ⚪ Not Started |
| App Launch | Dec 1, 2025 | Dec 15, 2025 | ⚪ Not Started |