## Sheet1
Story ID | Title | Description | Story Points | MoSCoW | Planned Week | Status | Critical Path | Dependencies | Assigned To | Time Spent (hrs) | Notes
US1 | Add to Cart from PDP/PLP | As Anjali, I want to add an item (with selected size/color) from product pages/lists so I can keep browsing without losing my selection. | 3 | Must Have | Week 1 | Done | Yes | None | Raj Patel | 10 | Completed Day 1
US2 | View & Edit Cart | As Rohan, I want to review my cart (size, price, qty, subtotal) so I can verify before checkout. | 5 | Must Have | Week 1 | In Review | Yes | US1 | Neha Sharma | 14 | Stuck in review 2 days - pricing API issue
US3 | Save for Later | As Anjali, I want to move items to Save for later so I can watch items without blocking checkout. | 5 | Could Have | Not Included | Not Started | No | Wishlist/Save Service, Auth/Anon Store | Unassigned | 0 | Deferred to Sprint 26
US4 | Price & Stock Revalidation | As Rohan, I want warnings for price/stock changes so I can decide confidently. | 5 | Must Have | Week 1 | Blocked | No | US2, Pricing Service, Inventory API | Backend Dev | 5 | Blocked by environment issue 2 days - DESCOPED
US5 | Promo Codes | As Anjali, I want to apply/remove coupons so I can unlock discounts. | 5 | Should Have | Not Included | Not Started | No | Promotions Engine, Pricing Service | Unassigned | 0 | Deferred to Sprint 26 - Kavita worked on this by mistake Days 1-3
US6 | Pincode & ETA Estimator | As Rohan, I want to check deliverability, fees, and ETA so I know when I'll receive the order. | 5 | Should Have | Week 1 | In Progress | No | Shipping Service, Pincode DB | Backend Dev | 12 | DESCOPED - Non-critical for MVP
US7 | Address Management | As Anjali, I want to add/edit/select a shipping address so delivery details are correct. | 5 | Must Have | Week 1 | In Progress | Yes | Address Service, Validation | Arjun Mehta | 18 | Day 4 in progress - 69% complete
US8 | Delivery Options & Fees | As Rohan, I want to choose standard/express shipping so I can balance cost and speed. | 3 | Should Have | Week 2 | Not Started | No | US6 | Unassigned | 0 | DESCOPED - Non-critical for MVP
US9 | Taxes & Price Breakdown | As Anjali, I want a clear breakdown (items, discounts, shipping, tax) so I trust the total. | 5 | Must Have | Week 1 | In Progress | Yes | US7, Tax Service, Pricing Service | Backend Team | 16 | Day 4 in progress - 62% complete - BLOCKING US10
US10 | Guest Checkout | As Anjali, I want to checkout as guest so I don't need an account first. | 8 | Must Have | Week 1-2 | Blocked | Yes | US7, US9, Checkout Orchestrator | Arjun Mehta + Team | 9 | Blocked by US9 dependency for 2 days - CRITICAL
US11 | 2-Step Fast Checkout | As Rohan, I want a two-step checkout with saved address/payment so I can finish quickly. | 8 | Should Have | Not Included | Not Started | No | US12, US7 | Unassigned | 0 | Deferred to Sprint 26
US12A | Payment Method - UPI Integration | Implement UPI payment intent flow with success/failure callbacks (split from US12) | 5 | Must Have | Week 2 | Not Started | Yes | US10, Payment Gateway | Kavita Rao | 0 | Split from US12 - Payment sandbox credentials pending 6 days
US13 | Payment Failure & Retry | As Rohan, I want safe retries on failure so I'm not double-charged or forced to start over. | 8 | Should Have | Not Included | Not Started | No | US12A | Unassigned | 0 | Deferred to Sprint 26
US14 | Order Confirmation | As Anjali, I want a confirmation page with order ID/summary so I know the purchase is complete. | 5 | Must Have | Week 2 | Not Started | Yes | US12A, Order Service | Frontend Dev | 0 | Required for sprint goal completion
US15 | Cart Persistence & Sync | As Rohan, I want cart persistence across sessions/devices so I can resume later. | 8 | Should Have | Not Included | Not Started | No | Cart Service, Auth, Sync Service | Unassigned | 0 | Deferred to Sprint 26
US16 | Inventory Recheck & Hold | As Anjali, I want recheck/temporary holds before payment so I don't pay for sold-out items. | 8 | Should Have | Not Included | Not Started | No | Inventory Service, Reservation System | Unassigned | 0 | Deferred to Sprint 26 - Technical dependency unclear
US17 | Price Lock & Rounding | As Rohan, I want price lock and consistent rounding so totals don't fluctuate. | 3 | Could Have | Not Included | Not Started | No | Pricing Service, Session Mgmt | Unassigned | 0 | Deferred to Sprint 26
US18 | Gift Options | As Anjali, I want gift message and optional wrap so I can send purchases as gifts. | 5 | Could Have | Not Included | Not Started | No | Gift Service, Pricing | Unassigned | 0 | Deferred to Sprint 26
US19 | Policies & Trust | As Rohan, I want clear returns/shipping/security info during checkout so I feel confident. | 2 | Could Have | Week 1 | Done | No | CMS/Policy Content | Siddharth Iyer | 6 | Completed Day 5
US20 | Accessibility & Performance | As Anjali, I want fast and accessible checkout so I can complete purchases on the go. | 13 | Won't Have | Not Included | Not Started | No | Performance Budget, A11y Standards | Unassigned | 0 | Cross-cutting concern - deferred as standalone story