## Sheet1
Story ID | Status | Days in Status | Time Spent (h)
US1 | Done | 1 | 10
US2 | In Review | 2 | 14
US7 | In Progress | 4 | 18
US19 | Done | 1 | 6
US9 | In Progress | 4 | 16
US4 | Blocked (env issue) | 2 | 5
US6 | In Progress | 3 | 12
US10 | Blocked (dependency on US9) | 2 | 9
US8 | Not Started | 6 | 0
US12A | Not Started (awaiting US10) | 6 | 0
US14 | Not Started (awaiting US12A) | 6 | 0